## Risk Register
Risk ID | Category | Risk Description | Regulation / Rule Reference | Likelihood | Impact | Risk Score | Current Controls | Control Effectiveness | Owner | Last Review Date | Next Review Date | Status | Notes
R-001 | Technology | AI tools used by employees without Technology Committee approval | AI Acceptable Use Policy; Rule 206(4)-7 | High | High | 9 | Technology Committee approval workflow; quarterly tool inventory audit | Partially Effective | Technology Committee | 2026-08-15 | 2026-09-30 | Needs Action | New AI policy effective 2026-09-01; initial inventory in progress
R-002 | Regulatory | AI-generated drafts not captured in books and records | Rule 204-2 (Books & Records) | High | High | 9 | Draft-retention directive; email archiving captures some outputs | Partially Effective | Laure B. | 2026-07-20 | 2026-10-01 | Needs Action | Gap: ChatGPT/Claude outputs not systematically archived
R-003 | Data Privacy | Client PII entered into external AI chat tools | Reg S-P; State privacy laws | High | High | 9 | AI policy prohibits PII in unapproved tools; training scheduled | Partially Effective | Laure B. | 2026-08-01 | 2026-09-23 | Active | Training sessions scheduled 9/23 and 9/25
R-004 | Vendor | AI vendor agreements lack required data-handling provisions | Rule 206(4)-7; Reg S-P | Medium | High | 6 | Vendor onboarding checklist; legal review of contracts | Partially Effective | Karl H. | 2026-06-30 | 2026-09-30 | Active | Claude and Copilot contracts under review; Anthropic MSA pending
R-005 | Regulatory | AI-assisted marketing materials not reviewed per Marketing Rule | Rule 206(4)-1 (Marketing Rule) | Medium | High | 6 | CCO pre-approval workflow for all client-facing materials | Effective | Laure B. | 2026-08-10 | 2026-11-10 | Monitoring | Process in place; need to add explicit AI-generation disclosure check
R-006 | Technology | Personal devices accessing firm data without MDM controls | Reg S-P; SEC Cybersecurity guidance | Medium | High | 6 | MDM enrollment required; conditional access policies in M365 | Partially Effective | IT Admin | 2026-07-15 | 2026-10-15 | Active | BYOD policy under revision; 3 unmanaged devices flagged in last audit
R-007 | Technology | M365 connector grants overly broad data access to third-party apps | Reg S-P; Data governance policy | Medium | High | 6 | Technology Committee connector approval process; scope review at onboarding | Partially Effective | Technology Committee | 2026-08-20 | 2026-10-20 | Active | D-044: Superfluid connector denied pending scope narrowing
R-008 | Regulatory | Meeting transcription tools recording without consent/disclosure | State wiretapping laws; Rule 204-2 | Medium | Medium | 4 | Verbal disclosure at meeting start; transcript retention policy | Partially Effective | Laure B. | 2026-08-05 | 2026-11-05 | Active | Need written consent protocol; varies by jurisdiction
R-009 | Regulatory | Inability to produce AI-related records promptly for SEC exam | Rule 204-2; Exam preparedness | Medium | High | 6 | Annual mock exam; document index maintained by compliance | Partially Effective | Laure B. | 2026-05-15 | 2026-09-15 | Needs Action | OVERDUE: AI records inventory not yet completed; mock exam did not cover AI
R-010 | Operational | Employees lack training on new AI acceptable use policy | Rule 206(4)-7; AI Policy | High | Medium | 6 | Training sessions scheduled; attendance tracking | Not Assessed | Laure B. | 2026-09-01 | 2026-09-25 | Active | First sessions 9/23 + 9/25; attestation required within 30 days
R-011 | Regulatory | Over-reliance on AI outputs without human review in advisory process | Advisers Act Sec. 206 (Fiduciary Duty) | Low | High | 3 | Human-in-the-loop policy; supervisor sign-off on AI-assisted recommendations | Effective | Karl H. | 2026-07-01 | 2026-10-01 | Monitoring | Policy documented; spot-check audits quarterly
R-012 | Technology | Personal AI accounts (ChatGPT, Claude) used on firm devices | AI Acceptable Use Policy; Reg S-P | High | Medium | 6 | Policy prohibition; endpoint monitoring for known AI domains | Partially Effective | IT Admin | 2026-08-25 | 2026-11-25 | Active | DNS filtering in place; browser-based bypass possible
R-013 | Technology | Unapproved browser extensions exfiltrating data or injecting content | Reg S-P; Cybersecurity policy | Medium | Medium | 4 | Extension whitelist in Chrome Enterprise; quarterly review of installed extensions | Effective | IT Admin | 2026-08-01 | 2026-11-01 | Monitoring | 14 extensions approved; GPO enforced on managed devices
R-014 | Data Privacy | Client data stored in non-US jurisdictions by cloud vendors | Reg S-P; Contractual obligations | Low | Medium | 2 | Vendor contracts specify US data residency; annual attestation | Effective | Karl H. | 2026-06-01 | 2026-12-01 | Monitoring | All current vendors US-only; re-verify at renewal
R-015 | Regulatory | Form ADV does not disclose AI tool usage in advisory services | Form ADV Part 2A | Medium | Medium | 4 | Annual ADV review; compliance calendar reminder | Partially Effective | Laure B. | 2026-03-31 | 2026-09-30 | Needs Action | OVERDUE: Next ADV amendment should include AI disclosure language
R-016 | Operational | AI tool outage disrupts critical business processes | Rule 206(4)-7; BCP policy | Low | Medium | 2 | BCP plan includes manual fallback procedures; no single-tool dependency | Effective | Karl H. | 2026-07-10 | 2026-01-10 | Monitoring | Annual BCP test passed; AI tools classified as non-critical
R-017 | Regulatory | AI tools processing MNPI without appropriate barriers | Insider Trading policies; Advisers Act | Low | High | 3 | Information barrier procedures; restricted list maintained; AI tools excluded from MNPI workflows | Effective | Laure B. | 2026-08-15 | 2026-11-15 | Monitoring | No AI tools currently have access to MNPI systems
R-018 | Regulatory | AI-generated trade recommendations bypass personal trading pre-clearance | Rule 204A-1; Code of Ethics | Low | Medium | 2 | Pre-clearance system mandatory; quarterly holdings reports | Effective | Laure B. | 2026-08-01 | 2026-11-01 | Monitoring | No incidents; process unchanged by AI adoption
R-019 | Vendor | Over-concentration in single cloud/AI vendor ecosystem (Microsoft) | Rule 206(4)-7; Vendor risk policy | Medium | Medium | 4 | Multi-vendor evaluation for critical services; annual concentration review | Partially Effective | Karl H. | 2026-06-15 | 2026-12-15 | Active | M365 + Copilot + Azure = deep Microsoft dependency; alternative eval underway
R-020 | Data Privacy | Sensitive data leakage through AI tool integrations and connectors | Reg S-P; Reg S-ID | Medium | High | 6 | DLP policies in M365; connector scope restrictions; Technology Committee review | Partially Effective | IT Admin | 2026-08-10 | 2026-11-10 | Active | DLP rules cover email/SharePoint; gap in Teams channel connectors
R-021 | Regulatory | AI-assisted calculations in Form PF reporting produce errors | Form PF | Low | High | 3 | Dual-calculation verification; senior analyst review before filing | Effective | Laure B. | 2026-04-30 | 2026-10-30 | Monitoring | Manual verification layer intact; AI tools not yet integrated into reporting
R-022 | Technology | SharePoint mapped drives expose folder structure to unauthorized apps | Reg S-P; Data governance policy | Medium | Medium | 4 | Conditional access policies; drive mapping restricted to managed devices | Partially Effective | IT Admin | 2026-09-08 | 2026-12-08 | Active | A-31: Mapped-drive exposure being escalated; Windows shell access a concern
R-023 | Regulatory | Social media posts drafted by AI lack required disclaimers | Rule 206(4)-1; Marketing Rule | Medium | Medium | 4 | Social media policy; CCO review of all posts; disclaimer templates | Effective | Laure B. | 2026-07-20 | 2026-10-20 | Monitoring | Approval workflow captures AI-drafted content; template updated 2026-Q3
R-024 | Operational | No documented incident response procedure for AI-specific data breaches | Reg S-P; SEC Cybersecurity rules | Medium | High | 6 | General IR plan exists; AI-specific scenarios not yet documented | Partially Effective | Karl H. | 2026-05-01 | 2026-09-30 | Needs Action | OVERDUE: AI scenario tabletop exercise planned for Q4
R-025 | Vendor | Third-party AI model updates alter outputs without notice, affecting advisory quality | Advisers Act Sec. 206; Vendor policy | Medium | Medium | 4 | Vendor notification requirements in contracts; periodic output validation | Partially Effective | Technology Committee | 2026-08-30 | 2026-11-30 | Active | Contract language under review; need model-versioning awareness protocol

## Risk Scoring Guide
Risk Scoring Matrix
Risk Score = Likelihood x Impact
| Low Impact (1) | Medium Impact (2) | High Impact (3)
High Likelihood (3) | 3 | 6 | 9
Medium Likelihood (2) | 2 | 4 | 6
Low Likelihood (1) | 1 | 2 | 3
Score Ranges
6 - 9 | High Risk | Immediate action required; escalate to senior management
3 - 4 | Medium Risk | Active monitoring; controls review within 30 days
1 - 2 | Low Risk | Acceptable risk level; routine monitoring
Control Effectiveness Definitions
Effective | Control consistently prevents or detects the risk; tested and verified
Partially Effective | Control addresses some aspects of the risk; gaps identified
Ineffective | Control does not adequately address the risk; remediation required
Not Assessed | Control has not yet been tested or evaluated
SAMPLE DATA — FOR WORKSHOP TESTING ONLY
This risk matrix contains fictional data. It does not represent any actual firm's compliance posture.